## Sheet1
Week | Task | Owned by | Deadline | Status | Notes
ASSIGNMENT 01 PLAN
Week 1 | Initialize and ideation | All members | 2017-10-15
| Meeting 1: inspiration board and brainstorming | All members | 2017-10-16
| Need finding: each member looks for ideas | All members | 2017-10-22 |  | Each member looks for observations throughout the week, and then share notes at the end of the week
| Research main ideas | Banu & Aya | 2017-10-18
| Meeting 2: inspiration board and brainstorming | All members | 2017-10-19
| Research idea: powerpoint casting | Aya | 2017-10-20
| Research idea: online therapist | Banu | 2017-10-21
| Research idea: panic app | Arukh and Mohammed | 2017-10-22
| Meeting 3: brainstorming | All members | 2017-10-15 |  | We meet up again some day during the week to check progress
| Agreement on idea due | All members | 2017-10-15 | Completed | Deadline for choosing topic. We agreed to use a virtual assistant
Week 2 | Research: Interaction Types | Banu | 2017-10-15
| Research: Aesthetics | Arukh | 2017-10-15
| Research: Statistical | Aya | 2017-10-15
| Research: Existing Virtual Assistants | Mohammed | 2017-10-15
| Interview planning | Aya | 2017-10-16 |  | Make a list of the types of people we need to interview
| Observe and interview | Arukh and Banu | 2017-10-16
| Document observations | Mohammed | 2017-10-17
| Make questionnaire 1 | Aya | 2017-10-17
| Conduct 5 minute surveys across the university | Aya | 2017-10-18
| Meeting 4: Share results and plan next steps | All members | 2017-10-19
| Write down user needs draft | Banu | 2017-10-17
| Make photo album and documentation folders | Mohammed | 2017-10-18
| Meeting 5: Finalize user needs and goals | All members | 2017-10-19
| Meeting 6: Point of view brainstorming and tea breaks | All members | 2017-10-20
| Meeting 7: Inspiration boards and documentation | All members | 2017-10-21
| Prototype draft ideas | Arukh and Banu | 2017-10-18
| Storyboard 1 | Mohammed and Arukh | 2017-10-18
| Storyboard 2 | Mohammed and Arukh | 2017-10-19
| Prototype 1 | Mohammed | 2017-10-20
Week 3 - Submission 1 Due | Prototype 2 | Arukh | 2017-10-21
| Document write-up | Banu | 2017-10-22
| Merge and prepare submissions | Aya | 2017-10-23
| SUBMIT ASSIGNMENT | Banu and Aya | 2017-10-24
ASSIGNMENT 02 IMPLEMENTATION PLAN
Week 4: 1. Heuristic Evaluation | Kick off meeting: discuss what's next | All members | 2017-11-05
| Methodology Review | All members | 2017-11-05
| Research Item: Nelson's Heuristics | Banu and Arukh | 2017-11-06
| Research Item: How to Receive Feedback | Aya and Mohammed | 2017-11-06
| Research Item: Types of plans & Implementation Plan | Aya | 2017-11-06
| Order screens and interactions | Arukh | 2017-11-06
| Design evaluation procedure | Banu | 2017-11-06
| Perform documented evaluation | All members | 2017-11-09
| Write evaluation result summary | Banu | 2017-11-10
| Write retrospective historical plan | Aya | 2017-11-11
| Research Item: GitHub functionalities | Banu and Arukh | 2017-11-12
| Update plan and time sheets | Aya | 2017-11-13
| Review discussion | All members | 2017-11-13 |  | Review all of the evaluation summary and assignment prompts
Week 5: 2. Skeleton and a Plan | Set up online meeting | All members | 2017-11-14
| Flesh out prototype design | Mohammed | 2017-11-15
| Implement screen interactions on website | Arukh | 2017-11-16
| Make GitHub Account | Arukh | 2017-11-17
| Online meeting: review | All members | 2017-11-18
| Prepare submission of first requirements set: evaluations | Banu | 2017-11-19
| Prepare submission of second requirements set: timelines | Aya | 2017-11-20
| Prepare submission of third requirements set: web prototype | Arukh | 2017-11-21
| Prepare future work suggestions | Mohammed | 2017-11-22
| Add Items to GitHub | All members | 2017-11-23